## hardware project
Hardware Project
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
September 2023
Name | Owner | Status | Due Date | Timeline - Start | Timeline - End | Priority | Last Updated | Dependency
Project Proposal | Nathaniel Lozano | Done | 2023-10-05 | 2023-09-20 | 2023-09-21 |  | Nathaniel Lozano Oct 3, 2023 04:04 PM
Bill of Materials | Nathaniel Lozano | Done | 2023-10-06 | 2023-09-20 | 2023-09-21 |  | Nathaniel Lozano Oct 3, 2023 04:19 PM | Project Proposal
Project Roadmap | Nathaniel Lozano | Working on it | 2023-10-07 | 2023-09-27 | 2023-10-04 | Critical ⚠️️ | Nathaniel Lozano Oct 3, 2023 04:19 PM | Bill of Materials, Project Proposal
|  |  | 2023-10-05 to 2023-10-07 | 2023-09-20 | 2023-10-04
October 2023
Name | Owner | Status | Due Date | Timeline - Start | Timeline - End | Priority | Last Updated | Dependency
Proof of purchase, KiCad | Nathaniel Lozano | Not Started | 2023-10-11 | 2023-10-04 | 2023-10-11 | Low | Nathaniel Lozano Oct 3, 2023 04:19 PM | Bill of Materials
Soldering, Laser Cutting | Nathaniel Lozano | Not Started | 2023-10-18 | 2023-10-11 | 2023-10-18 | Low | Nathaniel Lozano Oct 3, 2023 04:19 PM | Bill of Materials
|  |  | 2023-10-11 to 2023-10-18 | 2023-10-04 | 2023-10-18
November 2023
Name | Owner | Status | Due Date | Timeline - Start | Timeline - End | Priority | Last Updated | Dependency
Arrival of materials | Nathaniel Lozano | Not Started | 2023-11-01 | 2023-11-01 | 2023-11-01 | Critical ⚠️️ | Nathaniel Lozano Oct 3, 2023 04:19 PM | Proof of purchase, KiCad
Begin building the physical model | Nathaniel Lozano | Not Started | 2023-11-08 | 2023-11-01 | 2023-11-08 | High | Nathaniel Lozano Oct 3, 2023 04:20 PM | Soldering, Laser Cutting, Arrival of materials
Prepare the software integration | Nathaniel Lozano | Not Started | 2023-11-15 | 2023-11-08 | 2023-11-15 | High | Nathaniel Lozano Oct 3, 2023 04:13 PM
Implement communication between the software and the Raspberry Pi | Nathaniel Lozano | Not Started | 2023-11-16 | 2023-11-08 | 2023-11-15 | High | Nathaniel Lozano Oct 3, 2023 04:20 PM | Begin building the physical model, Prepare the software integration
Test for the model for functionality, address any issues | Nathaniel Lozano | Not Started | 2023-11-22 | 2023-11-15 | 2023-11-22 | Critical ⚠️️ | Nathaniel Lozano Oct 3, 2023 04:20 PM | Implement communication between the software and the Raspberry Pi
Optimize software performace with Raspberry Pi | Nathaniel Lozano | Not Started | 2023-11-23 | 2023-11-15 | 2023-11-22 | Medium | Nathaniel Lozano Oct 3, 2023 04:21 PM | Test for the model for functionality, address any issues
Prepare for the final presentation | Nathaniel Lozano | Not Started | 2023-11-29 | 2023-11-22 | 2023-11-29 | High | Nathaniel Lozano Oct 3, 2023 04:21 PM | Optimize software performace with Raspberry Pi, Implement communication between the software and the Raspberry Pi, Test for the model for functionality, address any issues
|  |  | 2023-11-01 to 2023-11-29 | 2023-11-01 | 2023-11-29
December 2023
Name | Owner | Status | Due Date | Timeline - Start | Timeline - End | Priority | Last Updated | Dependency
Final Presentation | Nathaniel Lozano | Not Started | 2023-12-06 | 2023-12-06 | 2023-12-06 | Critical ⚠️️ | Nathaniel Lozano Oct 3, 2023 04:21 PM | Prepare for the final presentation
|  |  | 2023-12-06 | 2023-12-06 | 2023-12-06